## Sheet1
| Activity | Start | End | Dur. | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13
1.1 | Perform survey with stakeholders | 1 | 10 | 10
1.2 | Prepare checklists | 11 | 25 | 15
1.3 | Feedback from stakeholders | 11 | 15 | 5
1.4 | Develop project specification | 16 | 35 | 20
2.1 | Create potential vendor’s list | 36 | 36 | 1
2.2 | Send invitation to tender | 37 | 39 | 3
2.3 | Organize conference and demo | 40 | 48 | 9
2.4 | Prepare product demo test cases | 40 | 45 | 6
2.5 | Select top four software vendors | 49 | 55 | 10
3.1 | Invite vendors for product demos | 56 | 56 | 1
3.2 | Invite vendors for interviews | 56 | 58 | 3
3.3 | Discuss details and prepare decision | 58 | 60 | 3
3.4 | Select final vendor | 61 | 62 | 2
3.5 | Negotiate contract | 63 | 64 | 2
3.6 | Sign up contract | 65 | 65 | 1