
Jan Rehwaldt, 2012-03-08, University of Tartu

Exercise 5, Project Management

|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | **Week number** | | | | | | | | | | | | | | | |
|  | **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** | **11** | **12** | **13** | **14** | **15** | **16** |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | **A** |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | B |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | **C** |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | **D** |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | schedule | |  | E |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | **X** | critical | |  |  |  | **F** |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | total float | |  |  |  |  | **G** |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  | **H** |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| **Resource** | **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** | **11** | **12** | **13** | **14** | **15** | **16** |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Analyst | **A** | **A** | **A** |  |  |  |  |  |  |  |  |  |  | **H** | **H** | **H** |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Designer I |  |  |  | **D** | **D** | **D** | **D** |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Designer II |  |  |  | B | **C** | **C** | **C** |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Developer I |  |  |  |  | E | E | E | **G** | **G** | **G** | **G** | **G** | **G** |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Developer II | --- | --- | --- | --- | --- | --- |  | **F** | **F** | **F** | **F** | **F** | **F** | --- | --- | --- |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

Activities marked in **bold** (A, D, G, H) may not be deferred, because they belong to the original critical path. **Bold and underlined** (C, F) activities became critical after assigning the available resources and may not be deferred under the given circumstances.

The activity network with those changes integrated is as follows.

****