Jan Rehwaldt, 2012-03-31, University of Tartu

Exercise 6, Task 1, Project Management

**Document existing System Desc.**

0

9

9

0

**0**

9

**Perform user survey**

 9

6

15

 9

**0**

15

**Find potential suppliers**

9

 4

13

16

 7

20

**Create test examples**

 15

2

 17

 15

**0**

 17

**Create volume figures**

15

 1

 16

16

 1

 17

**Create office layout**

15

 1

16

16

 1

 17

**Create invitation to tender**

17

 3

 20

17

**0**

 20

**Send invitation to tender**

20

 1

21

20

**0**

21

The **critical path** is marked in bold red – document existing system description -> perform user survey -> create test examples -> create invitation to tender -> send invitation to tender. Within this path all possible delays (floats) are 0.

The earliest possible finish date is after **21 days**.